## Meeting Inputs
Global Supply Management
Meeting Plan Checklist
AQE Input
Utilize Program Review Form -or -
Utilize Express Program Review Form
PPAP Requirements
R@R Timing and Requirements
Customer Specific Requirements
Introduction/Instructions to all Nexteer Supplier Websites.
Engineering Input
Latest part prints and specifications
Program Timing / Critical Characteristics
Technical Documents including sub-component drawings.
Program Information such as estimated annual usage, PPAP dates, SOP dates, etc.
Pilot and Prototype requirements and timing.
Key/Critical characteristics for PPAP
Buyer Input (from quote)
Packaging plan
Quoted Tool Capacity
Estimated Annual Volume
Supplier Input
Supplier Scorecard, be prepared to discuss
Updated supplier information (Supplier Profile) including contact list.
Program Timing including tooling, PPAP, R@R
Supplier issues/concerns caused by Nexteer.
Supplier issues/concerns not associated with Nexteer.
Questions/concerns needing to be addressed by Nexteer
Other Potential Supplier Input
Information on the manufacturing facility (Location, Capacity, etc.)
Preliminary Process Flow Diagram (PFD)
Preliminary Control Plan
Preliminary Timing Charts
Manufacturing Site Organizational chart
Subcontractors/Sub-Tier Mgt
Capability studies on similar parts.
Major disruptions, Problem Cases, PPM/Total Defects Reduction Plan
Tooling / Equipment Plans
Checking Fixture Plan
Prototype Plan
On-Going Product Assurance Testing
Preliminary PFMEA
Proof of Nexteer required quality certifications or transition plans (Should be posted in Supplier Profile)
Description of Operator Training program
Plan for communication between technical support and manufacturing plant.
Completed Team Feasibility Commitment
Error Proofing/ Poke-Yoke Techniques

## Program Review
PROGRAM REVIEW CHECKLIST
[6 empty] | Date of Review: | [14 empty] | New Risk Level of Product(s)
[6 empty] | Supplier : | [14 empty] | (Determine upon completion of Program Review)
Supplier Duns:
Supplier/Mfg Location:
|  |  | PART NUMBER |  |  |  | DESCRIPTION |  |  |  | MODEL |  |  |  | PLATFORM |  |  | HIGH VOLUME
[11 empty] | YEAR | START OF | [5 empty] | SCENARIO
[12 empty] | PRODUCTION | [5 empty] | (Vehicles)
1
2
3
4
5
6
CHECK IF IN ATTENDANCE
Nexteer Automotive
|  |  |  | TITLE | [5 empty] | NAME |  | PHONE |  |  |  | EMAIL
AQE
SQE
BUYER
PROGRAM MGR
PPAP COORDINATOR
COMPONENT ENGINEER
PRODUCT ENGINEER
RESPONSE TEAM
SUPPLIER CONTACTS
[10 empty] | NAME |  | PHONE |  |  |  | EMAIL
PRESIDENT
QUALITY MANAGER
KEY CONTACT
PPAP CONTACT
QUALITY CONTACT
RUN@RATE CONTACT
Highlight first column in color to indicate activity requirements.
LEGEND: |  |  | COMPLETE |  | (Ctrl-g) | [5 empty] | OPEN WITH RECOVERY PLAN |  |  | (Ctrl-y) |  |  |  | NO PLAN OR PLAN DOES NOT MEET PROGRAM TIMING |  |  |  | (Ctrl-r)
| A | Product Application Does the supplier have working knowledge of the following items? | [9 empty] | Issues Description and/or Sketch |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
| 1 | Intended use of product.
| 2 | End use application of product.
| 3 | Latest Prints and Specifications, Traceability
| 4 | Source restrictions specified by engineering.
| B | Design Review Identify characteristics that will require controls. (KPC's, KCC's, CQC's, QCI's) Ideally, a six sigma capability is the goal. Note gaps between desired and actual, with action plans to close. | [9 empty] | Issues Description and/or Sketch |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
| 1 | Critical dimensions and interfaces of product KPC's, KCC's, CQC's, QCI's, Pass-Through Characteristic/Feature
| 2 | Fit & Function, Safety Compliance
| 3 | Packaging Specification
| 4 | Labeling requirements
| C | Program Information List information required below | [9 empty] | Details |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
| 1 | Platform
| 2 | Model Year
| 3 | Estimated Annual Volume
| 4 | Supplier PPAP Due Date
| 5 | SOP
| 6 | Manufacturing Site
| 7 | Supplier Quoted Tool Capacity (5 days)
| D | Product Requirements & Timing Record the following if applicable. | [9 empty] | Details |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
| 1 | Prototype requirements.
| 2 | Pre-Production Requirements
| 3 | Other Product Requirements
| E | Supplier Tooling Requirements Develop a program review for the tooling supplier on critical components. | [9 empty] | Details |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
| 1 | Supplier Tooling Completion Dates
| 2 | Tooling Supplier Name (if different)
| F | Supplier Gage Review Mutual Agreement on gage concept proposal. Certify Gage to product design record. | [9 empty] | Details |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
| 1 | Development and Approval of Gage Design Plan
| 2 | Gage Evaluation including Measurement System Analysis (MSA)
| 3 | Gaging Completion Dates
| G | Product Measurement Plan Have acceptable measurement methods been confirmed and correlated? | [9 empty] | Details |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
| 1.1 | Has we received the supplier’s plan for dimensional layout and measurement of the component? (Should include the measurement methods, layout, datums, tools, equipment and fixtures (if applicable))
| 1.2 | Has engineering reviewed and approved the supplier plan for dimensional layout and measurement?
| 1.3 | Has the our Receiving Facility, reviewed and approved the supplier plan for dimensional layout and measurement? (Applicable for sites with a Receiving Inspection)
| 1.4 | Not applicable: The supplier has received dimensional accreditation by the using division.
| H | Capability Assessment Guidelines List Characteristic(s) to be used in capability study. | [9 empty] | Details |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
| 1.1 | KPC / QCI (note details in column)
| 1.2 | KPC / QCI (note details in column)
| 1.3 | KPC / QCI (note details in column)
| 2 | Capability Study Parameters
| 3 | Can your process meet Ppk =/> 1.33? Goal is 2.0
| 4 | Can your process meet Cpk =/> 1.67?
| I | Measurement System Analysis Guidelines Add equipment used for Capability Assessment and MSA requirements | [9 empty] | Details |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
| 1 | Measurement Equipment #1 & Methodology
| 2 | Measurement Equipment #2 & Methodology
| 3 | Measurement Equipment #3 & Methodology
| 4 | Measurement Equipment #4 & Methodology
| 5 | Measurement Equipment #5 & Methodology
| 6 | Measurement Equipment #6 & Methodology
| J | Design Responsible Suppliers List all issues/requirements if the supplier is design responsible. | [9 empty] | Details |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
| 1 | Was a Design Failure Modes & Effects Analysis (DFMEA) initiated by the supplier?
| 2 | Has our PDT reviewed the DFMEA?
| 3 | Are DFMEA open items addressed on an action plan and communicated to our PDT?
| K | PPAP Guidelines The link below will take you to the SUPPLIER PPAP SUBMISSION CHECKLIST. Utilize the Checklist for PPAP discussions. List potential issues below for tracking purposes. | [9 empty] | Details |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
|  | Link to SUPPLIER PPAP SUBMISSION REQUIREMENTS CHECKLIST (Use attached link or worksheet version provided.) | [10 empty] | https://portal.covisint.com/portal/cmdocs/f5c49c9346caad19ee48601f4445d602/appendix_20_1.xls
1
2
3
4
5
| L | First Time Quality (FTQ) Improvement Process | [9 empty] | Details |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
| 1 | FTQ Improvement Process Initiation Review our FTQ procedure and training presentations as required.
| 2 | FTQ Improvement Process Documentation Review the use of Gate Charts / Step Down Charts / Alarm Charts (Appendix 31_2 & 57_3)
| 3 | Check procedure or methods in place to comprehend FTQ documentation and improvement.
| 4 | Determine if preliminary data from supplier accurately depicts FTQ results.
| M | Run@Rate Requirements The link below will take you to the R@R Plan. Utilize the R@R Plan for discussions. List potential issues below for tracking purposes. | [9 empty] | Details |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
Link to Run@Rate Plan (Use attached link or worksheet version provided.)
[9 empty] | Run@Rate Plan |  |  | https://portal.covisint.com/portal/cmdocs/0a28eb96ac442d6cd12af7d06ad18c46/appendix_15.xls
[8 empty] | Run@Rate Worksheet |  |  |  | https://portal.covisint.com/portal/cmdocs/0a28eb96ac442d6cd12af7d06ad18c46/appendix_15.xls
1
2
3
4
5
| N | WEBSITE INFORMATION Determine the suppliers access and working knowledge of each database below. | [9 empty] | Details |  |  |  |  | Responsibility |  | Forecast Completion Date | Action Plan |  |  | Actual Completion Date | Progress
| 1 | Capability to access/update the following:
| 1.1 | Supplier Profiles (Discuss Red/Yellow/Green status)
| 1.2 | Supplier Suggestions Program (SSP/SCR)
| 1.3 | Supplier Scorecard (Updated copy if current supplier)
| 1.4 | Problem Solver
| 1.5 | Customer Specific Requirements / Quality Expectations
| 1.6 | Additional Forms & Procedures available on the website
| 2 | Registered to the Nexteer Automotive Supplier Website Mainly used for electronic PPAP submissions
| 2.1 | Initial electronic ppap submissions
| 2.2 | SSP/SCR required ppap submissions
appendix_6_1_Program_Review_Checklist Revised: October 5, 2009
End of file

## ProgRew Instructions
Global Supply Management
The following instructions are intended to help the AQE/SQE in performing the Program Review. Take a moment to review the Instructions. The intent of the program review is to engage the supplier in conversations about various aspects of the current program/parts and determine areas of concern that will need further action.
The form is protected/locked so that users can tab through fields. To allow attachments (such as program rosters) and/or additional information into any open field within the form, the form can be unprotected. The password is "unlock". This will allow each user to customize the program review to fit their needs while continuing to use a common form and process.
We will start the instructions with definitions and acronyms:
KPC | Key Product Characteristics
Most important product features or material properties for meeting customer requirements.
The two kinds of KPCs are 1) safety and compliance, and 2) fit and function. KPCs may be attributes (present or not).
It is required to target variable KPCs at nominal and reduce variation continuously because these characteristics are optimized at the nominal
specification and have a loss function associated with deviating from nominal.
KCC | Key Process Control Characteristic
Most important process characteristics that have a direct effect on the KPCs.
Suppliers may designate additional process characteristics as KCCs.
QCI | Quality / Customer Interface
A feature or property of a product that is contacted directly by the customer and has an immediate impact on their satisfaction
if not within limits. Or, a characteristic that does not meet the KPC criteria, but is deemed critical to the final product or its manufacturability.
QCC | Quality Control Characteristic
Most important process characteristics that have a direct effect on the QCI's. Suppliers may designate additional process characteristics as QCI's.
PPAP | Product Part approval process.
Pass-Through Characteristic
Is a characteristic/feature where an anomoly only declares itself under certain conditions such as environmental stimulation and cannot be tested
in our operations (i.e. soft tie rods, stepper motor with step loss and steering hose with incorrect rubber component.
The first part of the Program Review is an informational list used by us and the Supplier for better communication.
Fill in the following information as thoroughly as possible:
Date of Review
Supplier (include both the facility name and parent name where applicable)
Supplier Duns Code (this is in reference to the manufacturing site producing the product)
Supplier/Mfg Location
Part Numbers
PPAP Date
Description
Platform
Model Year
SOP Date
Supplier Contacts: (List key supplier contacts)
Key Contact
PPAP Contact
Quality Contact
Run@Rate Contact
Nexteer Automotive Contacts (List key Nexteer Automotive contacts)
AQE
SQE
Buyer
Program Manager
PPAP Coordinator
Component Engineer
Product Engineer
Response Team
New Risk Level of Product (Once the review has been completed, evaluate the program risk based on your findings)
Sections A through M are used to track the progress of the supplier through various aspects of building a new product. Each section
focuses on a specific area and is as comprehensive as possible.
The first columns will be used to color code each line item. Green indicates completed, Yellow indicates Open with recovery plan, Red indicates the suppliers process will not meet our requirements.
The formatting for these three colors has been automated. Go to the cell you want to change, then hit the following key:
for red use "Ctrl-r" for yellow use "Ctrl-y" for green us "Ctrl-g" this coding will also show up in black/white copies with patterns for each color.
.
The columns represented in each section are used to promote communication between us and the supplier. It also determines responsibility,
forecasts completion dates, action plans, actual completion dates and progress. Each block is expandable to add information as necessary.
The following gives an explanation of each section:
Section A | Product Application | Review how this will be used at our locations, at the customer, etc.
Section B | Design Review | Review prints/specs/ QCI/KPC, and pass-through characteristic/feature, packaging and labeling requirements.
Section C | Program Information | Review with supplier so they understand the final product and it's requirements.
Section D | Product Requirements & Timing | # of parts required, type of product (saleable vs non-saleable) to be recorded.
Section E | Supplier Tooling Requirements | Tooling completion and possible roadblocks should be discussed.
Section F | Supplier Gage Review | Evaluate and approve gage designs.
Section G | Product Measurement Plan | Consider the measurement req't and techniques that will be used for dimensional layout on the component prior to ppap.
Section H | Capability Assessment Guidelines | Determine based on the print requirements, customer requirements. Detail this section well.
Section I | Measurement Systems Analysis Guidelines | Based on the item listed in section H, detail equipment and methodologies that will be used.
Section J | Design Responsible Suppliers | If your supplier is responsible for the design, this section should be discussed.
Section K | PPAP Guidelines | Hyperlink to our PPAP checklist
Section L | First Time Quality (FTQ) Improvement Process | Training and or evidence of conformance is reviewed in this section.
Section M | Run@Rate Requirements | Hyperlink to our R@R plan
Section N | Website Information | Lists all websites and programs the supplier will need in working with Nexteer Automotive.
appendix_6_1_Program_Review_Checklist Revised: October 5, 2009

## Express
Global Supply Management
"Express" Program Review
Section A: Supplier Program Review
Part Number:
| Nexteer Automotive Information (From Roster Database & Request for Sourcing): |  |  |  |  | Family Parent Part No. (if any):
1 | Nexteer Automotive Start Of Production Date: |  |  |  |  | Prod. Mfg. Loc.:
2 | Volume Information |  | Year:
3 |  |  | Annual Usage:
4 |  |  | Peak Weekly Usage:
Forecasted Builds
5 |  |  | Type of Build:
6 |  |  | Parts required Date:
7 |  |  | Quantity:
8 |  |  | PML
9 |  |  | Build when PPAP is required:
10 |  |  | Supplier PPAP Due Date
11 |  |  | PPAP Level Required | 3
12 | Comments
Section B: Supplier Commitments (Supplier complete):
13 | Supplier First Parts Promise Date
14 | Estimated PPAP package delivery
15 | Supplier Quoted 5 Day Capacity
(vs. Peak Usage in question #4)
16 | The supplier is responsible to register and use our Supplier Websites and must be capable to update and access the following:
Supplier Profiles
Supplier Suggestion Program (SSP / SCR)
Problem Solver
Customer Specific Requirements/ Quality Expectations
IMDS system (reportable Chemicals)
17 | The Supplier agrees to and understands the following:
A. The only authorization to implement Nexteer Automotive engineering changes (including marked up prints) must be issued by our Buyer.
B. No change, of any kind, shall be made in material content, processing methods, testing methods, or location of manufacture without the
prior written approval of Steering Solutions Services Corporation.
Agreed by:
[5 empty] | Authorized representative |  | Date
18 | Supplier Comments/ Concerns:
Section C: Run @ Rate :
19 | Is Part Commodity Exempt? Y/N |  |  |  | Letter Location:
20 | Exemption Calc. (highest # 15 / # 4) |  |  |  | (if less than 40%, may exempt Run @ Rate)
21 | Approving Supplier Quality Manager |  |  |  |  | Date:
22 | Comments:
appendix_6_1_Program_Review_Checklist Revised: October 5, 2009

## Express Instructions
Global Supply Management
SPDP Express Form
Instructions
PRINT IN PORTRAIT MODE
l | SPDP Express forms should be filled in, transmitted, and stored electronically. Please use the part number as the first part of the filename and put a zero in front of 9 million part numbers (to achieve 8 digits and proper sort order by Windows Explorer).
l | The tab key can be used to move to the next available field in the form to enter data. Similarly, shift_tab will move to the previous available field.
For filling in the SPDP Express form:
l | Section A: Volume Information and Scheduled Builds (lines 1 to 10) should be filled in by the Product Engineer or the Program Team Leader. Line 11 will be filled in by the AQE.
l | Section B should be filled in by the Supplier (lines 13 to 18). Enter the Supplier Name in the appropriate cell and enter the name and date of the authorized Supplier Representative who is filling in the form.
l | Section C should be filled in by the AQE. If the part commodity is exempt (see Express form for criteria), it should be listed in the Commodity Exemption letter signed by the Supplier Quality Manager. This is expected to be one letter listing all exempted commodities and stored in one location for reference by all of Supplier Quality.
appendix_6_1_Program_Review_Checklist Revised: October 5, 2009